## Sheet1
Task Id | Task Name | Start Date | End Date | Duration(Days)
1 | Title Defense
1.1 | Topic Brainstorming | 2026-04-26 | 2026-04-26 | 1
1.2 | Topic Decision | 2026-04-27 | 2026-04-27 | 1
1.3 | Presentation Preparation and Division | 2026-04-28 | 2026-04-29 | 2
2 | Proposal Defense
2.1 | Literature Review and Figma Designing | 2026-04-30 | 2026-05-02 | 3
2.2 | UML Diagrams and Backlog | 2026-05-03 | 2026-05-05 | 3
2.3 | DFD Diagram | 2026-05-06 | 2026-05-07 | 2
2.4 | Preparation of Documentation and Presentation | 2026-05-08 | 2026-05-09 | 2
3 | Mid-Term Defense
3.1 | Correction of Diagrams and Project Work Division | 2026-05-14 | 2026-05-15 | 2
3.2 | Gantt chart | 2026-05-18 | 2026-05-18 | 1 |  | PROJECT SUBMISSION DEADLINE: 12 July
3.3 | Project Start
3.3.1 | Database Definition and Login/Signup Page | 2026-05-20 | 2026-05-22 | 3
3.3.2 | User Dashboard and Admin Dashboard redirection | 2026-05-23 | 2026-05-24 | 2
3.3.3 | Order Menu creation(For users) and Admin custom menu for daily "Today's special" unique menu | 2026-05-26 | 2026-05-28 | 3
3.3.4 | Order POST Logic and display order on admin side | 2026-05-28 | 2026-05-29 | 2 | (End here for now)
3.4 | Testing and Test Case Creation | 2026-05-30 | 2026-06-02 | 4 | Remaining: Order Tracking(Admin updates status, user sees updates)
3.5 | Documentation Correction | 2026-06-03 | 2026-06-04 | 2 | User Order History Tab, Marking items as Sold out(Admin side) and making it visible in user side
3.6 | Documentation for Mid-Term Defense Creation | 2026-06-05 | 2026-06-08 | 4
3.7 | Presentation Preparation and Division | 2026-06-12 | 2026-06-13 | 2 | (Mid-Defense in 15-Jun)